## Slide 1
Request to Proceed to EMC for Public Notice and Hearings with Proposed Rule Re-adoptions for Water Use Registration and Allocation Rules
Water Allocation Committee – January 13, 2021
Linwood Peele, DWR

## Slide 2: Rules – 15A NCAC 02E
Subchapter | Section | Description
02E | .0100 Section | General Provisions
02E | .0300 Section | Registration of Water Withdrawals and Transfers
02E | .0500 Section | Central Coastal Plain Capacity Use Area
02E | .0600 Section | Water Use During Droughts and Water Supply Emergencies

## Slide 3: Rulemaking – History
January 2017 2017 |  | EMC, APO date - Determinations for public Commence Rulemaking to re-adopt rules in accordance with APA
August 2017 May 2019 July 2019 |  | Rule drafts process halted after IBT lawsuit Rule drafts completed Updated the WAC on rules re-adoption timeline
Aug.-Oct. 2019 |  | RRC Pre-review rules
June 2020 |  | Rules updated to incorporate RRC comments
August 2020 |  | RRC accepted our deadline March 1, 2022 (.0100, .0300, .0500 & .0600) March 1, 2023 (.0400)

## Slide 4: Rulemaking – Schedule
January 2021 |  | WAC approves draft rules to full EMC (Sections .0100, .0300, .0500 & .0600)
March 2021 |  | EMC approves draft rules to public notice
April – June 2021 |  | Public comment period (notice and hearings)
July – September 2021 |  | Review comments/draft HO report
January 2022 |  | EMC adopts rules
February 2022 |  | RRC review/approval
March 1, 2022 |  | Proposed effective date

## Slide 5: Summary of Key Revisions
Technical Revisions
  Updated agency names and addresses
  Updated rule and statute citations
  Made minor edits for clarification
  Corrected typographical errors, punctuation
  Format changes
Substantive Revisions
  Clarified and/or updated selected rule language
  Removed language deemed unnecessary
  Updated rules per statutes, session law
  Repealed rules no longer needed.

## Slide 6: Summary of Key Revisions
02E .0100 – General Provisions
No change (02E .0106)
No change (02E .0107)

## Slide 7: Summary of Key Revisions
02E .0300 – General Provisions
Updated agency names and addresses (02E .0301)
Removed language already codified in G.S. 143-215.22H (02E .0301)
Removed incorrect reporting requirements already codified in G.S. 143-215.22H (02E .0301)

## Slide 8: Summary of Key Revisions
02E .0500 – Central Coastal Plain Capacity Use Area
Format changes and removed language deemed unnecessary (02E .0501)
Format changes and removed language deemed unnecessary. Updated language for clarification. (02E .0502)
Repealed rule. Removed language deemed unnecessary. (02E .0503)
Updated language for clarification. (02E .0504)
Format changes and removed language deemed unnecessary. (02E .0505)
Repealed rule. Removed language deemed unnecessary. (02E .0506)
Updated language for clarification. Added 3 definitions (aquifer recharge, cretaceous aquifer system zones, and recharge rate). (02E .0507)

## Slide 9: Summary of Key Revisions
02E .0600 – Water Use During Droughts and Water Supply Emergencies
No changes (02E .0601, .0604, .0605, .0608, .0610, .0611, & .0612)
Alphabetized the definitions, added definitions and reworded language for clarification. (02E .0602)
Updated language for clarification, updated rule cross-reference and added statutory authority to History Note. (02E .0603)
Updated language for clarification. (02E .0606, .0607, & .0609)
Updated language for clarification and updated rule cross-reference. (02E .0613, .0614, & .0615)

## Slide 10: Today’s Request:
WAC Approval of Water Use Registration and Allocation rule drafts to proceed to EMC for approval to go to public notice and hearings
Staff will complete regulatory impact analysis
Subchapter | Section | Rules | Description
02E | .0100 | .0106-.0107 | General Provisions
02E | .0300 | .0301 | Registration of Water Withdrawals and Transfers
02E | .0500 | .0501-.0507 | Central Coastal Plain Capacity Use Area
02E | .0600 | .0601-.0615 | Water Use During Droughts and Water Supply Emergencies

## Slide 11
Questions Related to CCPCUA
Gabrielle Chianese
Hydrogeologist, CCPCUA Permit Program
Ground Water Management Branch
Phone: 919-707-9008 gabrielle.chianese@ncdenr.gov
Linwood Peele, Supervisor
Water Supply Planning Branch
Division of Water Resources
Phone: 919-707-9024 linwood.peele@ncdenr.gov